## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurrence (1-10) | Risk Impact (1-10) | Risk Factor (1-10) | Risk Mitigation | Person in Charge of Tracking
server availability | we need a server for our app find a server | 8 | 9 | 7.2 | ask as many people if we know | All of us
bad time management | use our time otherwise under-/overestimate our work | 9 | 5.5 | 4.95 | look more on Jira | Joel
wrong priorization | doing (maybe) right tasks at the wrong time | 4 | 6 | 2.4 | look more on Jira | All of us
procrastination | doing important tasks "tomorrow" | 3 | 8 | 2.4 | gain discipline | All of us
underestimated complexity | thought work would be much easier | 4 | 3 | 1.2 | being flexible | Fabian/Yann
participation | not enough work for everyone | 6 | 2 | 1.2 | helping each other | All of us
lack of communication | not knowing what the others are working on | 1 | 5 | 0.5 | talking | All of us
UC | Name | Documentation [h] | Coding [h] | Testing [h] | Total [h] | FP
UC1 | Register | 2 | 4 | 3 | 9 | 57.12 | Upcoming
UC2 | LogIn/Out | 2 | 7 | 1.5 | 10.5 | 55.08 | Done
UC3 | View Memes | 3 | 7 | 5 | 15 | 49.98 | Done
UC4 | Upload/Delete.img | 1 | 3 | 2 | 6 | 44.88 | Upcoming
UC5 | show Profile | 1.5 | 2 | 1.5 | 5 | 32.64 | Done
UC6 | Creating Account | 2.5 | 5 | 2 | 9.5 | 57.12 | Upcoming
UC7 | Profiledata | 2 | 3 | 1 | 6 | 28.56 | Done
[7 empty] | Register | RET | DET | FTR | Count | Complexity | show Profile | RET | DET | FTR | Count | Complexity
[7 empty] | User Input |  | 5 | 0 | 5 | Low | User Input |  | 1 | 1 | 2 | Low
[7 empty] | User Output |  | 0 | 1 | 1 | Low | User Output |  | 1 | 1 | 2 | Low
[7 empty] | User Inquiries |  | 1 | 1 | 2 | Low | User Inquiries |  | 1 | 1 | 2 | Low
[7 empty] | Internal Files | 1 | 2 |  | 3 | Low | Internal Files | 0 | 1 |  | 1 | Low
[7 empty] | External Interfaces | 1 | 1 |  | 2 | Low | External Interfaces | 1 | 0 |  | 1 | Low
[7 empty] | FP | 57.12 |  |  |  |  | FP | 32.64
[7 empty] | LogIn/Out | RET | DET | FTR | Count | Complexity | Creating Account | RET | DET | FTR | Count | Complexity
[7 empty] | User Input |  | 2 | 1 | 3 | Low | User Input |  | 5 | 0 | 5 | Low
[7 empty] | User Output |  | 1 | 1 | 2 | Low | User Output |  | 0 | 1 | 1 | Low
[7 empty] | User Inquiries |  | 1 | 1 | 2 | Low | User Inquiries |  | 1 | 1 | 2 | Low
[7 empty] | Internal Files | 1 | 2 |  | 3 | Low | Internal Files | 1 | 2 |  | 3 | Low
[7 empty] | External Interfaces | 1 | 1 |  | 2 | Low | External Interfaces | 1 | 1 |  | 2 | Low
[7 empty] | FP | 55.08 |  |  |  |  | FP | 57.12
[7 empty] | View Memes | RET | DET | FTR | Count | Complexity | Profiledata | RET | DET | FTR | Count | Complexity
[7 empty] | User Input |  | 0 | 2 | 2 | Low | User Input |  | 0 | 2 | 2 | Low
[7 empty] | User Output |  | 2 | 1 | 3 | Low | User Output |  | 0 | 1 | 1 | Low
[7 empty] | User Inquiries |  | 2 | 2 | 4 | Low | User Inquiries |  | 1 | 1 | 2 | Low
[7 empty] | Internal Files | 1 | 1 |  | 2 | Low | Internal Files | 0 | 1 |  | 1 | Low
[7 empty] | External Interfaces | 0 | 1 |  | 1 | Low | External Interfaces | 0 | 1 |  | 1 | Low
[7 empty] | FP | 49.98 |  |  |  |  | FP | 28.56
[7 empty] | Upload/Delete.img | RET | DET | FTR | Count | Complexity
[7 empty] | User Input |  | 1 | 0 | 1 | Low
[7 empty] | User Output |  | 1 | 1 | 2 | Low
[7 empty] | User Inquiries |  | 2 | 1 | 3 | Low
[7 empty] | Internal Files | 1 | 1 |  | 2 | Low
[7 empty] | External Interfaces | 1 | 1 |  | 2 | Low
[7 empty] | FP | 44.88